Emergency Campaign to Save Central Israeli Forests – Interim Summary

Project 22437 – Eshtaol Forest and Park Ayalon-Canada

October 2025

In May 2025, some 2,000 hectares (or 5,000 acres) of forest and open space in central Israel were burnt, including some 1,500 ha. (3700 acres) of KKL-JNF forest land:

In Eshtaol Forest, about 760 ha. were burned, of these:

345 ha. were burned on 23.5.25

412 ha. were burned on 30.5.25

In Ayalon-Canada Park, 610 ha. were burned, all on 30.5.25.

The rehabilitation plan includes:

- Treatment and removal of burnt trees

- Removal of dangerous hazards

- Pruning for safety

- Regulating flow channels and preventing erosion

- Repairing access routes

- High-density plantings in damaged recreation and leisure areas

- Treatment of regenerating pine seeds

- Planning fire lines

- Establishing firebreaks

- Perennial care of invasive species

- Wildlife and vegetation surveys

Priorities and implementation were determined by a steering team of professionals from relevant fields. The rehabilitation process is expected to continue for 10-15 years, in gradual stages, based on surveys and insights gathered along the way, in accordance with the policy paper Rehabilitation after Extreme Events (2021) of the KKL-JNF Forestry Department.

Stages of Rehabilitation (Forestry Department, KKL-JNF)

Stage 1 – immediate (within a year after the event)

- Mapping the burn area and the extent of the damage

- Treatment of safety and other hazards

- Removal of hazardous trees

- Treatment of invasive species

Stage 2 – intermediate (1-4 years after)

- Continued treatment of other affected areas

- Preparation of an integrated plan for forest management and long-term rehabilitation

- Surveys, monitoring, area designation and prioritization, establishing firebreaks

- Plantings

Stage 3 – long term (4-20 years after)

- Completion of infrastructure repairs

- Implementation of the forest management plan (detailed planning and execution of vegetation rehabilitation across the entire forest area, based on the principles of the overall plan).

Note: The emergency campaign currently focuses on Stage 1

Cost Evaluation (July 2025)

|  | Eshtaol bloc | Estimated cost, incl. VAT, in shekels | Ben Shemen-Ayalon Canada Park bloc | Estimated cost, incl. VAT, in shekels | Yad Lashiryon surrounds, Latrun | Estimated cost, incl. VAT, in shekels |
| --- | --- | --- | --- | --- | --- | --- |
| Burnt area in hectares, approx. | 650 hectares |  | 600 hectares |  | 10 hectares |  |
| Forests | Eshatol Forest |  | Ayalon Canada Park Forest |  |  |  |
| Removal of hazards (trees near roads and access areas) and cleaning |  | 6,500,000 |  | 6,000,000 |  | 100,000 |
| Control of invasive species |  | 250,000 |  | 150,000 |  | 0 |
| Immediate repair of fences and signs |  | 20,000 |  | 50,000 |  | 12,000 |
| Concrete base for equipment storage container |  |  |  | 22,000 |  |  |
| Subtotal |  | 6,770,000 |  | 6,222,000 |  | 112,000 |
| Total | 13,104,000 |  |  |  |  |  |

Rehabilitation activities until now:

- About 70% of the areas defined as “highly urgent” have been treated

- Immediate hazards have been removed

- In preparations to develop a plan to manage the remaining plots and plan new firebreaks

- Maintenance of roads

- Planning the treatment of invasive species

- Planting plan – will be based on the 2026 surveys and will be prepared towards the winter of 2027

- Renewed growth and flowering have been observed

Eshtaol Forest

A plan is being developed for follow-up treatments on secondary roads

Ayalon-Canada Park

- Rehabilitation is complex due to managing the park’s opening to the public

- Planned action: to create a leisure and tourism area in the heart of the park, and continuing rehabilitation work on its periphery. A work plan will be developed.

- Mine clearance – carried out using a dedicated demining system, to be completed before the park opens

Nature strips along Road 1

- Removal of burnt trees in cooperation with Netivei Israel (Israel Roads)

- KKL-JNF will treat invasive species and remove burnt trees

- This activity has become a focus for donation in the framework of Project 22437.

Plan for Treatment of Burnt Trees (2026):
Recommendation: Treatment of enclosed areas (narrow, small, and between roads) and areas designated for future firebreaks.
Discussion on the reallocation of firebreak zones in the Eshtaol Forest and Ayalon-Canada Park.
The steering committee convenes once every 4–6 weeks.

Attachments:

- Link to photo folder

- Presentation on Ayalon-Canada Park – Highway 1 (English)

- Map of Eshtaol Forest fires

- Map of fires and areas for fundraising in Ayalon-Canada Park along Highway 1

- Eshtaol Forest LATAM brochure

- Article by Yoav Lin

- Video by Yoav Lin

קרן קימת לישראל

Keren Kayemeth LeIsrael-Jewish National Fund

Resource Development and External Affairs Division

Marketing Department